1
2
3
4
5
6
7
8
9
10
11
12
19
20
13
14
15
16
17
18
Design Database
#3 – 3
Program Database
#4 - 3
Connect Database
#5 - 3
Test Database
#6 - 3
Design Home
#8 - 2
Program Home
#9 - 3
Program Search Bar
#10 - 2
Write User Manual Home
#11 – 1
Design Post Ad
#13 - 1
Program Post Ad
#14 - 2
Write User Manual Post
#15 - 1
Design View Ad
#17 - 1
Program View Ad
#18 - 3
Write User Manual View
#19 - 1
Design Profile
#21 - 1
Program Profile
#22 - 2
Write User Manual Profile
#23 - 1
Ex. A.T. on All Pages
#24 - 1

---
1, 6,
10, 13,
16
5, 9,
12, 15
18, 19
2
3
4
20
7
8
11
14
17
Design Database
#3 – 3
Program Database
#4 - 3
Connect Database
#5 - 3
Test Database
#6 - 3
Design Home
#8 - 2
Program Home
#9 - 3
Program Search Bar
#10 - 2
Write User Manual Home
#11 – 1
Design Post Ad
#13 - 1
Program Post Ad
#14 - 2
Write User Manual Post
#15 - 1
Design View Ad
#17 - 1
Program View Ad
#18 - 3
Write User Manual View
#19 - 1
Design Profile
#21 - 1
Program Profile
#22 - 2
Write User Manual Profile
#23 - 1
Ex. A.T. on All Pages
#24 - 1